## WAVIVI Launch Checklist
Done | Category | Task | Owner | Notes
| Backend / Auth | Verify live Supabase keys in Vercel production env vars (not just .env.local)
| Backend / Auth | Test signup -> login -> password reset end-to-end on the deployed URL
| Backend / Auth | Confirm RLS is on for every table; verify a second user can't see the first's data
| Backend / Auth | Grep for SUPABASE_SERVICE_ROLE in client components - must be zero hits
| Backend / Auth | Realtime chat: subscribe/unsubscribe on route change, no leaks
| Mock data | Replace places.ts, tools.ts, and other hardcoded arrays with Supabase queries (or confirm intentional for launch)
| Mock data | Burn down the ~185 TODO/FIXME/MOCK markers
| Mock data | Profile page shows the real signed-in user, not hardcoded 'John'
| Recommendation engine | Decide: ship rule-based now, or wire AI (Anthropic SDK) before launch?
| Security | Run npm audit and fix high/critical vulns
| Security | Rate-limit signup + AI endpoints
| Security | Disable / gate dev-only routes in production (/api/design-overrides, scrape endpoints)
| PWA / performance | Run npm run build - must be clean
| PWA / performance | Test 'Add to Home Screen' on real iOS + Android
| PWA / performance | Lighthouse PWA score >= 90
| PWA / performance | Run npm run optimize:images on all public/ assets
| Legal | Privacy Policy page live
| Legal | Terms of Service page live
| Legal | Cookie / consent banner if targeting EU users
| Analytics & errors | Wire analytics (Vercel Analytics or Posthog)
| Analytics & errors | Wire error monitoring (Sentry)
| UX polish | Finish typography migration so size bumps propagate cleanly
| UX polish | Walk every page on a real phone; note tiny/overlapping/off-brand text
| UX polish | Empty states + loading skeletons for async pages
| Pre-deploy gate | npx tsc --noEmit - 0 errors
| Pre-deploy gate | npm run lint - clean
| Pre-deploy gate | Custom domain + SSL configured in Vercel
| Pre-deploy gate | Production env vars all set
| Day-of launch | Take a Supabase backup right before launch
| Day-of launch | Rollback plan written down (revert commit + redeploy)